## Sheet1
|  | Elsa | Devynn | Avery | Andrea
Tues Mar 19 | Define project scope | X | X | X | X
Thurs Mar 21 | Create timeline (as requested by Sneha) | X | X | X | X
| Obtain API access for Spotify and Genius | X | X | X | X
| Extract popularity of songs across decades from Spotify (50s, 60s, 70s, 80s, 90s, 00s, 10s, US Top 50) | X |  | X | X
| QA/QC results from decade pull |  |  | X | X
| Create dictionaries of tracks | X |  | X | X
| Export text results | X |  | X | X
| Create code to connect to Genius and extract lyrics as text |  | X
Sat Mar 23 | Extract lyrics from Genius |  | X
Organize lyrics by decade
Create dataframe of results
Extract most popular words
QA/QC and data cleanup
Tues Mar 26 | Create charts
Analysis and conclusions
Thurs Mar 28 | Finalize presentation | X | X | X | X
Sat Mar 30 | Presentation Day | X | X | X | X